## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
How to Draw in the LCD for the PG12 board | 70 | 20 | 1400 | 2023-03-23 |  | R | Got to understand from Will's Lab
Platform/Slider Physics | 70 | 40 | 2800 | 2023-03-23 |  | M | Implemeted Slider interaction + have necessary idea to implement physics
Main Physics + Integrations | 70 | 70 | 4900 | 2023-03-23 |  | O | Another big ticket item
Satchel Physics | 3 | 8 | 24 | 2023-03-23 |  | O | Needs to get this resolved soon(info+eqs underway)
Initial Setup | 8 | 3 | 24 | 2023-03-23 |  | M | Understood + have clarity as to what the scope is
Capstone Project | 70 | 40 | 2800 | 2023-04-07 |  | O | End stages of a huge Capstone Project delivery by 28th April
Using LCD to draw shapes and stuff | 13 | 20 | 260 | 2023-04-07 |  | O | Now drawing the castle,satchel etc + refreshing everytime
Implement Rail Gun | 40 | 8 | 320 | 2023-04-07 |  | O | Kinda have an idea needs more exploring
Implement LED | 40 | 13 | 520 | 2023-04-07 |  | O | Did'nt think much of it now but need to mitigate it soonish(End Item)

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100