## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
How to Draw in the LCD for the PG12 board | 70 | 20 | 1400 | 2023-03-23 |  | O | Have to experiment with the library Glib to draw and mitigate it
Platform/Slider Physics | 70 | 40 | 2800 | 2023-03-23 |  | O | Fist thing I will probably tackle , very important for the game
Main Physics + Integrations | 70 | 70 | 4900 | 2023-03-23 |  | O | Another big ticket item
Satchel Physics | 40 | 40 | 1600 | 2023-03-23 |  | O | Need to experiment with physics equation
Initial Setup | 8 | 3 | 24 | 2023-03-23 |  | M | Understood + have clarity as to what the scope is
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100